## Weekly Progres
12.08.2022
Contract | Sectorul de drum | Lungimea, km | Valoarea contractului | Antreprenor | Compania de monitorizare | Banca finanțatoare | Începutul contractului | Progresul fizic
Programul sectoarelor de drum (Drumuri naționale)
RSPSP/W4/01 | R1 Chișinău - Ungheni - Sculeni, km 6+446 - km 24+050 | 17.6 | 23 111 340.27 Euro | Euro-Asian Construction Corporation EVRASCON JSC (Azerbaijan) | WSP and TECNIC | BEI | 2014-07-08 | 95.79%
RSP/W5/01 | R1 Chișinău - Ungheni - Sculeni, km 74+177 - km 96+200 | 22 | 15 065 241.04 Euro | Euro-Asian Construction Corporation EVRASCON JSC (Azerbaijan) | Spea Ingegneria | BERD | 2014-07-11 | 93.83%
RSP/W6/03 | R16 Bălți - Fălești - Sculeni, LOT I 1 sect. km 4+800 - km 30+270; | 25.47 | 50 599 020.54 Euro | Impresa Pizzarotti & C.S.p.A (Italy) | Louis Berger | BEI | 2016-05-02 | 99.99%
RSP/W6/04 | R16 Bălți - Fălești - Sculeni, LOT II 2 sect. km 30+270 - km 59+480 | 29.21 | [5 empty] | 96.2%
RSP/W9/01 | R1 ocolirea s. Bahmut, km 68+250 - km 74+177 | 8 | 5 325 090.37 Euro | Rutador SRL (Moldova) | Rendel Limited | CE FIV | 2018-10-05 | 71.16%
RSP/W9/02 | M3 Porumbrei - Cimișlia km 0+000 - km 19+010 | 19 | 29 903 744.46 Euro | ONUR A.S. | Eptisa | BEI | 2019-01-02 | 91.88%
RSP/W9/03 | M3 ocolirea mun. Comrat, km 0+000 - km 18+263 | 18.3 | 29 497 220.74 Euro | ONUR A.S. |  | BEI | 2019-01-02 | 92.32%
RSP/W9/05 | M3 ocolirea s. Slobozia Mare, km 0+000 - km 18+290 | 18.3 | 18 284 398.77 Euro | Metag Isaat Ticaret A.S | IRD | BERD | 2019-05-27 | 42.69%
RSP/W10/01 | M3 Chișinău - Giurgiulești, km 96+800 - km 122+800; km 122+800 - km 151+200; LOT 1 | 54.4 | 29 932 873.89 Euro | Automagistral-Pivden LLC | Eptisa | BERD | 2019-02-01 | 99.96%
| M3 Chișinău - Giurgiulești, km 151+200 - km 171+290; km 179+650 - km 190+750. LOT 2 | 31.2 | [5 empty] | 76.32%
RSP/W11/01 | R6 Chișinău - Orhei - Bălți, km. 99+530 - km. 111+230 - LOT I | 11.7 | 36 003 933.09 Euro | ONUR A.S. | IRD | BERD | 2020-03-12 | 99.62%
RSP/W11/02 | R6 Chișinău - Orhei - Bălți, km. 76+700 - km. 94+700 și podul la km. 72+944 - LOT II | 18 | [5 empty] | 84.34%
RSP/W11/03 | M2 ocolirea mun. Chișinău km 0+000 - km 6+550 | 6.5 | 9 917 975.17 Euro | JV Rutador SRL și Lusmecon SRL | Tecnic Egnatia Odos | BEI | 2019-09-22 | 66.87%
RSP/W12/01 | R34 Hîncești - Leova - Cahul, 1 sect. km 0+000 - km 42+200; | 42 | 56 495 268.42 Euro | Ozka Inșaat AȘ | IRD | BERD | 2020-08-24 | 20.51%
RSP/W12/02 | R34 Hîncești - Leova - Cahul, 2 sect. km 42+200 - km 83+000 | 40.8 | [5 empty] | 26.69%
TOTAL , km |  | 362.48
Programul sectoarelor de drum (Drumuri locale)
LRIP/W2/02 | L405, R21 - Onișcani km 0+000 - km 9+962 | 9.9 | 88 289 715.59 MDL | JV Nouconst & Nirom-roz | TECNIC HILL SWEROAD | BM | 2019-09-18 | 99.5%
LRIP/W5/01 | Sector 1.1: G46: Dobrușa – Ignăței – Scorțeni – Codrul Nou – R14 (km 22+610 – km 29+200) and Section 1.2: G46: Dobrușa – Ignăței – Scorțeni – Codrul Nou – R14 (km 29+200 – km 35+622,09) | 13 | 103 729 144.73 MDL | ANT Insaat | TECNIC HILL SWEROAD | BM | 2020-09-28 | 62.7%
LRIP/W5/02 | Sector 2.1: G46: Dobrușa – Ignăței – Scorțeni – Codrul Nou – R14 (km 15+760 – km 22+610) and Section 2.2: G47: R9 – Olișcani – Peciște – Ignaței – G46 (km 12+880 – km 18+075 | 12.2 | 150 121 517.07 MDL |  |  |  | 2020-09-28 | 54.2%
LRIP/W5/03 | Sector 3.1: G49: G47 – Peciște – Trifești – R20 (km 0+00 – km 6+560) and Section 3.2: G49: G47 – Peciște – Trifești – R20 (km 6+560 – km 11+426,70) | 11.4 | 110 257 600.92 MDL |  |  |  | 2020-09-28 | 21.4%
LRIP/W5/04 | L390 Pîrlița - Nisporeni (km 0+000 – km 10+900) | 10.9 | 84 184 919.25 MDL | Rutador SRL | TECNIC HILL SWEROAD |  | 2020-09-21 | 83%
LRIP/W6/01 | G105: R3 - Costești - Ţipala - G106 (km 0+000 - km 8+450) | 8.4 | 98 435 373.58 MDL | Rutador SRL | TECNIC HILL SWEROAD | BM | 2020-12-01 | 70.9%
LRIP/W6/02 | G105: R3 - Costești - Ţipala - G106 (km 8+450 - km 17+350) | 8.9 | 94 947 821.00 MDL | Nouconst SRL (Moldova) | TECNIC HILL SWEROAD |  | 2020-12-01 | 98.5%
LRIP/W6/03 | G105: R3 - Costești - Ţipala - G106 (km 17+350 - km 26+400) | 9 | 81 831 658.02 MDL | SRL Irinda-Prim |  |  | 2020-12-01 | 59%
LRIP/W6/04 | G105: R3 - Costești - Ţipala - G106 (km 26+400 - km 34+584) | 8.2 | 87 963 811.12 MDL | SRL Irinda-Prim |  |  | 2020-12-01 | 81%
TOTAL |  | 91.9

## Type of Works
Types Of Works
• General Requirements | • Preparatory Works | • Earhworks | • Pavement | • Bridges And Overpasses | • Drainage Structures | • Incidental Construction | • Road Marking And Signing | • Engineering Services | • Slip Remedial Works | • Dayworks
• Provide and furnish contract office | • Site Preparation | • The Execution of Earthworks | • Cold Recycling Of The Asphalt Concrete Pavements | • Preparatory Works, Site Installation, Accommodation Of Trafic | • Culverts And Drainage Facilities | • Crash Barriers | • Permanent Traffic Control | • Rearrangement Of Power Lines. Road Illumination | • Slip Remedial Works | • Labour
• Provide site laboratory including office for The Engineer | • Site Clearance | • The Execution of Ditches | • Asphalt Pavement Milling | • Abutment/Piers | • Cleaning, Reconditioning And Repairing Existing Inlets, Outlets, Drains, Spillways And Chutes |  | • Permanent Road Marking | • Rearrangement Of Communication Lines |  | • Materials
• Traffic Management | • Demolition | • Shaping And Planting Of Slopes and Excavated Surfaces | • Widening And Reconstruction Of The Existing Carriageway And Provision Of New Pavement | • Technical Support | • Paved Waterways |  | • Sidewalks | • Bus Stops |  | • Equipment
• Insurances And Performance Guarantee | • Temporary Road and Signing | • Planting Of Trees And Shrubs | • Prime And Tack Coats For Supporting Surface | • Repair of concrete surfaces | • Minor Concrete Structures |  | • Roundabout | • Rearangement Of Gas Pipeline
• Compliance With Environmental Management Plan Requirements | • Removal Of The Old Road Structure | • Roundabout | • Asphalt Concrete For Pavements | • Removal of existing structures | • Open Drains, Side Drains |  |  | • Rearangement Of WS And Sewage
|  | • Minor intersections | • Removing, Restoring And Repairing The Shoulders | • Repaire To Abutment Earthworks | • Protection Work
|  | • Entries Into The Yards | • Cement-Stabilized Base Works | • Construction Of Bridge Substructure | • Kerbs
|  | • Bypass | • Coated Macadam | • Superstructure | • Drains, Manholes, Exit Gully
|  | • Sidewalks | • Various Asphalt Works | • Bridge Approach | • Safety Barriers
|  | • Protection of Shoulders | • Minor Intersections | • Expansion Joints | • Discharges
|  |  | • Entries Into The Yards | • Waterproofing
|  |  | • Parking Lot | • Safety Barriers
|  |  | • Bypass | • Surface Water Disposal
|  |  | • Interchange | • Embankment Slope Protection
|  |  | • Sidewalks | • Asphalt Concrete Pavement
|  |  | • Roundabout | • Pedestrian Bridge Railing
|  |  | • Pavement Patching | • Slab To Bridge Deck, Bridge Walkway, Parapet And Concrete Slope Layer
• Concrete Repair
• Miscellaneous
• Bridge Repairs
• Access Stairs on Slopes
• Bored Piles